## Requirements_Traceability
SAR SHIP DETECTION PROJECT - FUNCTIONAL REQUIREMENTS TRACEABILITY MATRIX
Req ID | Category | Requirement Title | Description | Tracker Subtask(s) | Week | Milestone | Priority | Status | Test Criteria
REQ-SYS-OUT-001 | System Output | Output Details | Output ship bounding boxes, class labels, and unique tracking IDs | ST-12.1, ST-17.1 | 6, 9 | Reporting, Final UI | P1-Critical | Not Started | JSON contains bbox coords, labels, IDs; UI displays overlays
REQ-USER-INPUT-002 | User Input | User Selection | Select coordinates, date, and area on map for ship detection | ST-08.1, ST-03.3 | 4, 2 | UI/UX Base | P1-Critical | Not Started | User can select ROI on map; API receives correct coordinates
REQ-USER-INPUT-003 | User Input | Input SAR | Allow users to upload custom SAR imagery for detection | ST-16.2, ST-04.3 | 8, 2 | Hardening | P2-High | Not Started | System accepts .tiff, .png, .jpeg; rejects invalid formats with error
REQ-SYS-DOWNLOAD-004 | Downloads | Download Full Image | Download annotated image with detected ships as .jpg | ST-12.1, ST-17.1 | 6, 9 | Reporting, Final UI | P2-High | Not Started | User receives .jpg with bounding boxes and labels
REQ-SYS-DOWNLOAD-005 | Downloads | Download Single Ship | Download individual ship crops as separate .jpg files by ID | ST-12.2 | 6 | None | P2-High | Not Started | User can download ship crop by ID; margin included
REQ-SYS-DOWNLOAD-006 | Downloads | Download JSON Data | Download JSON with bbox coords, width, class, and ID | ST-12.1, ST-12.3 | 6 | Reporting | P1-Critical | Not Started | JSON file contains all metadata; <10s generation time
REQ-SYS-PROC-007 | Processing | Ignore Land | Exclude land from processing; keep visible in output | ST-06.1, ST-06.2, ST-06.3 | 3 | Land Separation | P1-Critical | Not Started | Land mask generated; ships on land filtered; land visible in output
REQ-SYS-PROC-008 | Processing | Image Preprocessing | Remove speckles and enhance during preprocessing | ST-05.1, ST-05.2 | 3 | Signal Denoising | P1-Critical | Not Started | CNR gain ≥35%; final output shows original, not preprocessed
REQ-SYS-PROC-009 | Processing | Polarization Choice | Use alternative polarization if VV unavailable | ST-04.1, ST-02.2 | 2, 1 | Correction | P1-Critical | Not Started | System detects polarization; falls back to VH if needed
REQ-SYS-DET-010 | Detection | Ship Detection | Detect only ships in SAR imagery | ST-07.1, ST-07.2 | 4 | Core ML Training | P1-Critical | Not Started | mAP@0.5 ≥95.6%; single-class detection
REQ-SYS-DET-011 | Detection | Respond & Display | Display ships with bounding boxes, labels, and IDs | ST-08.2, ST-17.1 | 4, 9 | Final UI | P1-Critical | Not Started | UI shows annotated image with all detections
REQ-SYS-DET-012 | Detection | Avoid Confusion | Avoid false positives from non-ship objects | ST-15.2, ST-13.2 | 8, 7 | None | P2-High | Not Started | False positive rate <14.7%; oil rigs filtered
REQ-SYS-DET-013 | Detection | Any Polarization | Detect ships regardless of polarization band | ST-04.1 | 2 | Correction | P1-Critical | Not Started | Detection works on VV, VH, and other bands
REQ-SYS-REPORT-014 | Error Handling | No Ships Report | Report when no ships detected; don't upload image | ST-08.3 | 4 | None | P2-High | Not Started | System displays 'No ships found' message instead of blank image
REQ-SYS-REPORT-015 | Error Handling | Format Error | Report error for incompatible file formats | ST-04.3, ST-16.2 | 2, 8 | Hardening | P2-High | Not Started | Clear error message for invalid formats; supported formats listed
REQ-SYS-REPORT-016 | Error Handling | Bad Connection | Handle timeouts and return error message | ST-16.1 | 8 | Hardening | P2-High | Not Started | Process stops after timeout; user notified
REQ-SYS-REQUEST-017 | Error Handling | User Queue | Implement FIFO queue with position tracking | ST-03.2 | 2 | None | P1-Critical | In Progress | Queue shows position; wait time <30s per user
REQ-DARK-AIS-001 | Dark Vessel | AIS Data Integration | Integrate AIS data for cross-verification | ST-09.1, ST-09.2 | 5 | Fusion Engine | P1-Critical | Not Started | AIS data loaded; timestamp synchronized
REQ-DARK-DET-002 | Dark Vessel | Dark Vessel Detection | Detect vessels not broadcasting AIS signals | ST-14.1 | 7 | Anomaly Det. | P1-Critical | Not Started | Non-broadcasting vessels flagged; confidence scores provided
REQ-DARK-LOC-003 | Dark Vessel | Location Matching | Spatial correlation within 1km radius | ST-09.1 | 5 | Fusion Engine | P1-Critical | Not Started | Haversine distance <1km; matches identified
REQ-DARK-ANAL-004 | Dark Vessel | Suspicious Activity Analysis | Analyze patterns like AIS disabling, STS transfers | ST-14.2, ST-14.3 | 7 | None | P2-High | Not Started | Loitering detected; STS transfers identified; heatmaps generated
REQ-DARK-INPUT-005 | Dark Vessel | External Dataset Support | Support historical and real-time AIS datasets | ST-09.2 | 5 | None | P2-High | Not Started | Historical AIS imported; real-time feeds supported
REQ-DARK-REPORT-006 | Dark Vessel | Dark Vessel Alerts | Generate alerts with time, location, confidence | ST-14.1, ST-09.3 | 7, 5 | Anomaly Det. | P1-Critical | Not Started | Alerts contain timestamp, coords, confidence; UI distinguishes dark vs confirmed
REQ-DARK-VALID-007 | Dark Vessel | False Alarm Mitigation | Multi-source validation and filtering | ST-15.2, ST-13.2 | 8, 7 | None | P2-High | Not Started | False alarm rate <0.2% open ocean; multi-source checks implemented

## Coverage_Summary
COVERAGE SUMMARY
Category | Total Requirements | Mapped Subtasks | Coverage %
System Output | 1 | 2 | 200%
User Input | 2 | 3 | 150%
Downloads | 3 | 3 | 100%
Processing | 3 | 6 | 200%
Detection | 4 | 6 | 150%
Error Handling | 4 | 5 | 125%
Dark Vessel Detection | 7 | 8 | 114.3%
TOTAL | 24 | 33 | 137.5%
KEY METRICS
Total Functional Requirements: | 24
Requirements with Subtasks: | 24
Requirements Missing Subtasks: | 0
Overall Coverage: | 137.5%
Critical (P1) Requirements: | 17
High (P2) Requirements: | 7

## Test_Criteria
TEST CRITERIA & SUCCESS METRICS
Req ID | Requirement | Test Method | Success Criteria | KPI Target | Validation Week
REQ-SYS-OUT-001 | Output bounding boxes, labels, IDs | Automated validation | JSON schema validated; all fields present | 100% schema compliance | W6
REQ-USER-INPUT-002 | Map selection | Manual + Integration test | Coordinates correctly passed to API | 100% accuracy | W4
REQ-USER-INPUT-003 | Upload SAR | Unit test | Valid formats accepted; invalid rejected | 100% format validation | W8
REQ-SYS-DOWNLOAD-004 | Download full image | Integration test | Image file created and downloadable | 100% success rate | W6
REQ-SYS-DOWNLOAD-005 | Download ship crops | Automated test | Individual crops generated with margins | 100% crop accuracy | W6
REQ-SYS-DOWNLOAD-006 | Download JSON | Performance + validation | JSON generated in <10s with all metadata | <10s, 100% complete | W6
REQ-SYS-PROC-007 | Land masking | Visual + automated | Land filtered from detections; visible in output | 0 land detections | W3
REQ-SYS-PROC-008 | Preprocessing | CNR measurement | Noise reduced; contrast enhanced | CNR gain ≥35% | W3
REQ-SYS-PROC-009 | Polarization handling | Unit test | System adapts to available bands | 100% band detection | W2
REQ-SYS-DET-010 | Ship detection | Benchmark test | Single-class detection verified | mAP@0.5 ≥95.6% | W4, W8
REQ-SYS-DET-011 | Display detections | Visual verification | UI shows all detected ships with annotations | 100% displayed | W9
REQ-SYS-DET-012 | Avoid false positives | Confusion matrix | Oil rigs and non-ships filtered | FP rate <14.7% | W8
REQ-SYS-DET-013 | Multi-polarization detection | Dataset test | Detection works on VV, VH, HH bands | Recall ≥90% all bands | W8
REQ-SYS-REPORT-014 | No ships report | Edge case test | System message displayed instead of blank image | 100% correct response | W4
REQ-SYS-REPORT-015 | Format error | Negative test | Invalid formats rejected with clear message | 100% error handling | W8
REQ-SYS-REPORT-016 | Timeout handling | Load test | Connection timeout triggers error message | 100% timeout capture | W8
REQ-SYS-REQUEST-017 | Queue management | Concurrency test | FIFO order maintained; position displayed | Wait <30s/user | W2
REQ-DARK-AIS-001 | AIS integration | Data validation | AIS data loaded and synchronized | 100% data ingestion | W5
REQ-DARK-DET-002 | Dark vessel detection | Benchmark test | Non-broadcasting vessels flagged | Detection rate ≥90% | W7
REQ-DARK-LOC-003 | Spatial correlation | Distance calculation | Matches within 1km radius identified | Accuracy ±50m | W5
REQ-DARK-ANAL-004 | Suspicious activity | Pattern analysis | Loitering and STS detected | 80% pattern detection | W7
REQ-DARK-INPUT-005 | AIS dataset support | Data pipeline test | Historical and real-time data processed | 100% compatibility | W5
REQ-DARK-REPORT-006 | Dark vessel alerts | Alert validation | Alerts contain all required metadata | 100% metadata complete | W7
REQ-DARK-VALID-007 | False alarm mitigation | Precision test | Multi-source validation reduces FP | FP <0.2% open ocean | W8